

**Capstone Project Report**

**Report 2 – Project Management Plan**

– HoChiMinh, January 2025 –

**Table of Contents**

[**I. Record of Changes 2**](https://docs.google.com/document/d/1s8HFidZ8yuxF3WaHulKK6btyay36wwqXp9Y1pZdmMa0/edit?hl=vi&tab=t.0#heading=h.sebqxsl9h39l)

[**II. Project Management Plan 3**](https://docs.google.com/document/d/1s8HFidZ8yuxF3WaHulKK6btyay36wwqXp9Y1pZdmMa0/edit?hl=vi&tab=t.0#heading=h.jk97gk73fd3k)

[1. Overview 3](https://docs.google.com/document/d/1s8HFidZ8yuxF3WaHulKK6btyay36wwqXp9Y1pZdmMa0/edit?hl=vi&tab=t.0#heading=h.r6x4mehnhju8)

[1.2 Project Objectives 10](https://docs.google.com/document/d/1s8HFidZ8yuxF3WaHulKK6btyay36wwqXp9Y1pZdmMa0/edit?hl=vi&tab=t.0#heading=h.w2k8ud31fqip)

[1.3 Project Risks 10](https://docs.google.com/document/d/1s8HFidZ8yuxF3WaHulKK6btyay36wwqXp9Y1pZdmMa0/edit?hl=vi&tab=t.0#heading=h.jufdsxgocibb)

[2. Management Approach 11](https://docs.google.com/document/d/1s8HFidZ8yuxF3WaHulKK6btyay36wwqXp9Y1pZdmMa0/edit?hl=vi&tab=t.0#heading=h.267fokm6186p)

[2.1 Project Process 11](https://docs.google.com/document/d/1s8HFidZ8yuxF3WaHulKK6btyay36wwqXp9Y1pZdmMa0/edit?hl=vi&tab=t.0#heading=h.2cz23hcmfgcu)

[2.2 Quality Management 11](https://docs.google.com/document/d/1s8HFidZ8yuxF3WaHulKK6btyay36wwqXp9Y1pZdmMa0/edit?hl=vi&tab=t.0#heading=h.jgg10btnyau1)

[2.3 Training Plan 12](https://docs.google.com/document/d/1s8HFidZ8yuxF3WaHulKK6btyay36wwqXp9Y1pZdmMa0/edit?hl=vi&tab=t.0#heading=h.jb67f229zitu)

[3. Project Deliverables 12](https://docs.google.com/document/d/1s8HFidZ8yuxF3WaHulKK6btyay36wwqXp9Y1pZdmMa0/edit?hl=vi&tab=t.0#heading=h.lprx7friv1qx)

[4. Responsibility Assignments 13](https://docs.google.com/document/d/1s8HFidZ8yuxF3WaHulKK6btyay36wwqXp9Y1pZdmMa0/edit?hl=vi&tab=t.0#heading=h.kjqmoyaipjzx)

[5. Project Communications 14](https://docs.google.com/document/d/1s8HFidZ8yuxF3WaHulKK6btyay36wwqXp9Y1pZdmMa0/edit?hl=vi&tab=t.0#heading=h.96lkqprdzvek)

[6. Configuration Management 15](https://docs.google.com/document/d/1s8HFidZ8yuxF3WaHulKK6btyay36wwqXp9Y1pZdmMa0/edit?hl=vi&tab=t.0#heading=h.buibke14xcdq)

[6.1 Document Management 15](https://docs.google.com/document/d/1s8HFidZ8yuxF3WaHulKK6btyay36wwqXp9Y1pZdmMa0/edit?hl=vi&tab=t.0#heading=h.t3cj0ws4n3hh)

[6.2 Source Code Management 15](https://docs.google.com/document/d/1s8HFidZ8yuxF3WaHulKK6btyay36wwqXp9Y1pZdmMa0/edit?hl=vi&tab=t.0#heading=h.mgnujqrvc2qd)

[6.3 Tools & Infrastructures 16](https://docs.google.com/document/d/1s8HFidZ8yuxF3WaHulKK6btyay36wwqXp9Y1pZdmMa0/edit?hl=vi&tab=t.0#heading=h.t1gehwsq43vk)

# I. Record of Changes

|  |  |  |  |
| --- | --- | --- | --- |
| Date | A\*  M, D | In charge | Change Description |
| 17/01/2025 | A\* | Luan |  |
| 20/01/2025 | A | Luan |  |
| 21/01/2025 | A | Luan | **Table of Contents** |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |

\*A - Added M - Modified D - Deleted

# II. Project Management Plan

## 1. Overview

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| ***WBS Item*** | ***Functionature*** | ***Function*** | ***Complexity*** | ***Est. Effort (man-days)*** |
| *1* | *Specification* |  |  |  |
| *1.1* |  | *Stakeholder register* | *Simple* | *3* |
| *1.2* |  | *Requirement definition* | *Medium* | *5* |
| *1.3* |  | *Project planning* | *Medium* | *5* |
| *1.4* |  | *Deliver report 1 - Project Introduction* | *Medium* | *4* |
| *1.5* |  | *Deliver report 2 - Project Management Plan* | *Medium* | *4* |
| *1.6* |  | *Deliver report 3 - System Requirement Specification* | *Complex* | *8* |
| *2* | *Design* |  |  |  |
| *2.1* |  | *Development tools selection* | *Simple* | *2* |
| *2.2* |  | *Database design* | *Complex* | *8* |
| *2.3* |  | *Design UI prototypes* | *Medium* | *5* |
| *2.4* |  | *Software design document* | *Complex* | *8* |
| *3* | *Web application for Admin* |  |  |  |
| *3.1* | *Function-01* | *Login* | *Simple* | *2* |
| *3.2* | *Function-01* | *Logout* | *Simple* | *1* |
| *3.3* | *Function-02* | *View personal profile* | *Medium* | *3* |
| *3.4* | *Function-02* | *Update personal profile* | *Medium* | *3* |
| *3.5* | *Function-02* | *Change password* | *Medium* | *2* |
| *3.6* | *Function-03* | *View user (manager)* | *Simple* | *1* |
| *3.7* | *Function-03* | *Add user (manager)* | *Simple* | *1* |
| *3.8* | *Function-03* | *Update user (manager)* | *Simple* | *1* |
| *3.9* | *Function-03* | *Delete user (manager)* | *Simple* | *1* |
| *3.10* | *Function-04* | *View price* | *Medium* | *3* |
| *3.11* | *Function-04* | *Update price* | *Medium* | *3* |
| *3.12* | *Function-05* | *View vehicle category* | *Simple* | *1* |
| *3.13* | *Function-05* | *Add vehicle category* | *Simple* | *1* |
| *3.14* | *Function-05* | *Update vehicle category* | *Simple* | *1* |
| *3.15* | *Function-05* | *Delete vehicle category* | *Simple* | *1* |
| *3.16* | *Function-06* | *View vehicle information* | *Medium* | *2* |
| *3.17* | *Function-06* | *Add vehicle information* | *Medium* | *2* |
| *3.18* | *Function-06* | *Update vehicle information* | *Medium* | *2* |
| *3.19* | *Function-06* | *Delete vehicle information* | *Medium* | *2* |
| *3.20* | *Function-07* | *Edit road* | *Complex* | *5* |
| *3.21* | *Function-07* | *Add stop station* | *Complex* | *5* |
| *3.22* | *Function-07* | *Update route* | *Complex* | *5* |
| *3.23* | *Function-07* | *Add route* | *Complex* | *5* |
| *3.24* | *Function-08* | *Edit recipe* | *Complex* | *5* |
| *3.25* | *Function-08* | *View money* | *Complex* | *5* |
| *4* | *Web application for Manager* |  |  |  |
| *4.1* | *Function-09* | *Login* | *Simple* | *2* |
| *4.2* | *Function-09* | *Logout* | *Simple* | *1* |
| *4.3* | *Function-10* | *View driver* | *Medium* | *3* |
| *4.4* | *Function-10* | *Add driver* | *Medium* | *2* |
| *4.5* | *Function-10* | *Update driver* | *Medium* | *2* |
| *4.6* | *Function-10* | *Delete driver* | *Medium* | *2* |
| *4.7* | *Function-11* | *View customer* | *Simple* | *1* |
| *4.8* | *Function-12* | *View booking* | *Simple* | *2* |
| *4.9* | *Function-13* | *Edit driver schedule* | *Medium* | *5* |
| *4.10* | *Function-14* | *View feedback* | *Simple* | *1* |
| *4.11* | *Function-14* | *Respond to feedback* | *Medium* | *2* |
| *5* | *Mobile application for Driver* |  |  |  |
| *5.1* | *Function-15* | *Login* | *Simple* | *0,5* |
| *5.2* | *Function-15* | *Logout* | *Simple* | *0,5* |
| *5.3* | *Function-16* | *View booking* | *Medium* | *2* |
| *5.4* | *Function-16* | *Accept booking* | *Medium* | *2* |
| *5.5* | *Function-16* | *View route* | *Medium* | *2* |
| *5.6* | *Function-17* | *View personal schedule* | *Medium* | *3* |
| *5.7* | *Function-17* | *Check-in* | *Medium* | *2* |
| *5.8* | *Function-17* | *Check-out* | *Medium* | *2* |
| *5.9* | *Function-18* | *Chat* | *Medium* | *5* |
| *6* | *Web application for Customer* |  |  |  |
| *6.1* | *Function-19* | *Login* | *Simple* | *2* |
| *6.2* | *Function-19* | *Logout* | *Simple* | *1* |
| *6.3* | *Function-20* | *Rent by hour* | *Complex* | *5* |
| *6.4* | *Function-20* | *Rent by route* | *Complex* | *5* |
| *6.5* | *Function-20* | *Share routes* | *Complex* | *5* |
| *6.6* | *Function-20* | *Share on-demand bridge* | *Complex* | *5* |
| *6.7* | *Function-21* | *Real-Time Ride Tracking* | *Complex* | *10* |
| *6.8* | *Function-22* | *Rating* | *Medium* | *3* |
| *6.9* | *Function-22* | *Feedback* | *Medium* | *2* |
| *6.10* | *Function-23* | *Alerts* | *Medium* | *3* |
| *6.11* | *Function-23* | *Notifications* | *Medium* | *2* |
| *6.12* | *Function-24* | *View profile* | *Medium* | *3* |
| *6.13* | *Function-24* | *Update profile* | *Medium* | *2* |
| *6.14* | *Function-25* | *Chat* | *Medium* | *5* |

***Testing***

|  |  |  |  |
| --- | --- | --- | --- |
| *WBS Item* | *Testing Stage* | *Complexity* | *Est. Effort (man-days)* |
| *T1* | *Unit testing* | *Medium* | *6* |
| *T2* | *Integration testing* | *Medium* | *6* |
| *T3* | *System testing* | *Medium* | *6* |

***Closing***

|  |  |  |  |
| --- | --- | --- | --- |
| *WBS Item* | *Activity* | *Complexity* | *Est. Effort (man-days)* |
| *C1* | *User guide* | *Medium* | *5* |
| *C2* | *Final report* | *Medium* | *5* |

***Total Estimated Effort (man-days): 180***

### 1.2 Project Objectives


|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **#** | **Testing Stag** | **Testing**  **Coverage** | **No. of Defects** | **% of Defect** | **Notes** |
| 1 | Reviewing | 50% | 12 | 20 |  |
| 2 | Unit Test | 60% | 12 | 10 |  |
| 3 | Integration Test | 50% | 12 | 30 |  |
| 4 | System Test | 50% | 12 | 30 |  |
| 5 | Acceptance Test | 60% | 12 | 10 |  |

### 1.3 Project Risks

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| ***#*** | ***Risk Description*** | ***Impact*** | ***Possibility*** | ***Response Plans*** |
| *1* | *Team members drop out* | *Critical* | *Medium* | *Reduce or change scope  Find new member* |
| *2* | *VPS stop running* | *Critical* | *High* |  |
| *3* | *Third party API not working* | *Critical* | *Low* |  |

## 2. Management Approach

### 2.1 Project Process



***Source****:* [*https://www.scrum.org/learning-series/what-is-scrum/*](https://www.scrum.org/learning-series/what-is-scrum/)

### 2.2 Quality Management

***Vin Shuttle*** *is developed and managed based on the Scrum model. The reason we decided to use this model is because:*

* ***Enhanced Collaboration and Communication***
* ***Accelerated Project Delivery with Iterative Development***
* ***Flexibility and Adaptability to Change***
* ***Continuous Improvement through Regular Reflection***

*In this project, to improve the project quality, we use the following approach:*

***API Convention***

* *Name the API Route that maps to the entity in the system.*
* *Each API response must return the following general information:*
  + *Status Code: 200, 400, 403, 404, etc.*
  + *ErrorCode: 201, 401, etc.*
  + *Success: True, False*
  + *Status Text: Not Found, Success, etc.*
  + *Total: Number of data items returned*
  + *Data: An array that contains all data items*

***Coding Convention***

* *Set meaningful names for variables.*
* *Add comments to the code if necessary to avoid confusion.*
* *Use Pascal casing for naming Enums, Classes, Interfaces, and Attributes.*
* *Use Camel casing for naming variables.*

***Unit Testing****: Each member has the responsibility to write a unit test to ensure a function/method works appropriately.*

***Integration Testing****: After finishing coding one module/screen, both members working on the client-side and server-side need to execute integration testing to ensure the module/screen can work smoothly from the client-side to server-side.*

***System Testing****: After finishing coding for the whole system, all team members need to re-execute all test cases and free tests to ensure the system is stable.*

### 2.3 Training Plan

|  |  |  |  |
| --- | --- | --- | --- |
| Training Area | Participants | When, Duration | Waiver Criteria |
| NextJS | All member | 10days | Mandatory |
| NestJS | All member | 10days | Mandatory |
| React Native | All member | 7days | Mandatory |
| Git/Github | All member | 1day | Mandatory |

## 3. Project Deliverables

|  |  |  |  |
| --- | --- | --- | --- |
| **No** | **Delivery** | **Due day** | **Note** |
| 1 | Project plan | 06/01/2025 | Make project goal plan |
| 2 | Report 1 | 15/01/2025 | Project introduction |
| 3 | Report 2 | 20/01/2025 | Project management plan |
| 4 | Report 3 |  | Software requirement specification |
| 5 | Report 4 |  | Software design document |
| 6 | Report 5 |  | Test case document, test documentation |
| 7 | Report 6 |  | Software user guides |
| 8 | Report 7 |  | Appendix |
| 9 | Code package 1 |  | Features for landing page web interface |
| 10 | Code package 2 |  | Features for business web application |
| 11 | Code package 3 |  | Features for admin web application |
| 12 | Code package 4 |  | Features for mobile application |
| 13 | Code package 5 |  | Final code package and document |

## 4. Responsibility Assignments

*D~Do; R~Review; S~Support; I~Informed; O- Omitted*

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Responsibility** | **Luan** | **Nhat** | **Quang** | **Khanh** | **Mentor** |
| Collect and specify user requirements | S | D | D | S | R |
| Analyse project requirements | S | D | D | S | R |
| Find solutions and fix problems that arise | S | D | D | S | R |
| Specify system features | I | D | D | S | R |
| Business analysis team guide | D | I | D | S | R |
| Manage members' tasks | S | S | D | I | R |
| Support members to solve problems | D | S | D | I | R |
| Design Interface of web, app | D | I | S | D | R |
| Database design | S | D | D | I | R |
| Implement interactions for the user interface | D | S | I | D | R |
| Create Test view point, test plan, test cases | S | I | S | D | R |
| Execute test, manage bugs | S | S | I | D | R |
| Write test report | S | S | I | D | R |

## 5. Project Communications

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Communication Item** | **Who/Target** | **Purpose** | **When, Frequency** | **Type, Tool, Method(s)** |
| Daily meeting | Team members | Review project progress  Discuss and solve problems  Discuss about project’s  business | Every workday | Discord, Messenger |
| Meeting supervisors | Supervisors and team members | Review project progress  Review project document,  core flows  Technical support  Give advice and direction | Every weekends | Google meet, zalo, FPTU |

## 6. Configuration Management

### 6.1 Document Management

*Because of the real-time data synchronization, we use Google Drive to manage documents. Google Drive allows team members to conveniently collaborate in real- time. We create documents on Google Drive based on the document template, then divide the document writing work for members based on their predefined responsibilities. Each member can see the results of the other members' work instantly.*

### 6.2 Source Code Management

*Creating git for frontend, backend, mobile. In one source project, we created a dev branch or branch based on members to build features. After that, we made a pull request from the current branch to the master or main branch that is deployed into the server. During pull request, merged codes will be sent to the server for passing pipelines and accept merge thereafter.*

### 6.3 Tools & Infrastructures

|  |  |
| --- | --- |
| **Category** | **Tools / Infrastructure** |
| **Technology** | Nextjs (FrontEnd), React Native (App), NestJS(BackEnd) |
| **Database** | MongoDB |
| **IDEs/Editors** | Visual Studio Code, MongoDBCompass |
| **Diagramming** | DrawIO, Visual paradigm/Visual paradigm online |
| **Documentation** | Ms Office, Google Docs/Sheets/Slides, Canvas |
| **Version Control** | Github (Source Codes), Google Drive (Documents) |
| **Deployment server** | Vercel |
| **Project management** | Github |